## Sheet1
| QRV on-boarding schedule | [7 empty] | Entry Date | 2018-06-18
Sprint | Week | Objective | Control | Topic | Day | Date |  | Detail | Type | Duration (h) | Ref. | Description | Trainer | Hours
1 | 1 | Basics |  | Tools & Libraries | 1 | 2018-06-18 | AM | MyELCA introduction I - MyELCA | Formal training | 2 | C-N-02 |  | LAT | 2
[8 empty] | MyELCA introduction II - QHB Introduction | Formal training | 2 | C-N-04.1 |  | QHD | 2
[7 empty] | PM | On-boarding program introduction | Introdution | 1 |  | Introduction from coach | Coach | 1
[8 empty] | Setup environment - Maven | Self training | 3 | R1
[5 empty] | 2 | 2018-06-19 | AM | Eclipse Debugging | Self training | 4 | E-T-26
[7 empty] | PM | JAVA | Self training | 4 | E-T-65 | Read JAVA-1.0.doc
[5 empty] | 3 | 2018-06-20 |  | JAVA | Self training | 8 | E-T-65
[6 empty] | 2018-06-21 | AM | JAVA checkpoint | Q&A | 1 |  | Check the fundamental programing and the differences among collections | Coach | 1
[7 empty] | PM | JAVA | Self training | 7 | E-T-65
[5 empty] | 5 | 2018-06-22 |  | JAVA | Self training | 8 | E-T-65
[6 empty] | 2018-06-23 | AM | Buffer for necessary training (JIRA, My ELCA) | Buffer | 0
1 | 2 |  | Q&A | Exercises | 1 | 2018-06-25 | AM | JAVA | Self training | 2 | E-T-65
[7 empty] | PM | JAVA-Exercise | Practice | 6 | E-T-65
[6 empty] | 2018-06-26 | AM | JAVA-Exercise | Practice | 4 | E-T-65
[7 empty] | PM | Q&A | Q&A | 3 |  | Check & explain on Maven, Eclipse, JAVA - Exercise | Coach | 3
[8 empty] | Coding convention | Self training | 1 |  | Read SunCodeConventions.pdf
[6 empty] | 2018-06-27 | AM | Javascript | Self training | 7 | E-T-11 | JS self-training point 1, 2, 3, 4, 6, 7
[7 empty] | PM | Q&A | Q&A | 1 | E-T-06 | Check & explain about Spring core | Coach | 1
[5 empty] | 2 | 2018-06-28 | PM | ReactJS | Self training | 8 | E-T-06
[5 empty] | 3 | 2018-06-29 | AM | ReactJS | Self training | 8 | E-T-06
[5 empty] | 4 | 2018-06-30 | AM | Buffer for necessary training (JIRA, My ELCA) |  | 0
2 | 3 | Frontend + Project WallBoard |  | UI design & Testing | 1 | 2018-07-02 |  | ReactJS | Self training | 8 | E-T-06
[6 empty] | 2018-07-03 | AM | ReactJS | Self training | 3 | E-T-06
[8 empty] | Q&A | Q&A | 1 |  | Check & explain Spring MVC, Coding convention | Coach | 1
[7 empty] | PM | Introduce exercise context for: BKH - Concepts (Topic: Multi-tiers, Multilingual) BKH - Programming (Topic: Exception handling & Design patterns, OOP) | Introdution | 1 |  | To give the trainee the context / scope before doing the exercise | Coach | 1
[8 empty] | Multi-tiers, Multilingual - Exercises | Self training | 3 | EB1
[6 empty] | 2018-07-04 |  | OOP & Design patterns & Exception handling - Exercises | Self training | 8 | EB1 | Powerpoint version
[5 empty] | 2 | 2018-07-05 | AM | Q&A | Q&A | 4 |  | Check & explain BKH | Coach | 4
[7 empty] | PM | CSS3 | Self training | 4 | E-T-12 | CSS self-training point 1,2,4,6,8,9,14 with the exercises inside each topic mention in the link.
[5 empty] | 3 | 2018-07-06 | AM | CSS3 | Self training | 6 | E-T-12
[7 empty] | PM | HTML5 | Self training | 2 |  | HTML self-training
[5 empty] | 6 | 2018-07-07 | AM | Buffer for necessary training (JIRA, My ELCA) |  | 0
2 | 4 |  | Q&A | UI Implementation | 1 | 2018-07-09 | AM | HTML5 | Self training | 7 |  | HTML self-training
[7 empty] | PM | Q&A | Q&A | 1 |  | Check JS | Coach | 1
[6 empty] | 2018-07-10 | AM | Coding best practices (for Web) | Reading | 2 |  | - JS: o General programming: 2101 , 2102, 2104, 2105. o Optimization: 2203. o Language specialties: 2301, 2302, 2303, 2309. o Security: 2401. - HTML: 3001. - CSS: 4001. | APL | 2
[8 empty] | Project WallBoard - Setup & Requirement clarification | Practice | 2 |  | Check out code from SVN, JIRA assignment | APL | 2
[7 empty] | PM | Project WallBoard - Implementation | Practice | 4
[5 empty] | 2 | 2018-07-11 |  | Project WallBoard - Implementation | Practice | 8
[5 empty] | 3 | 2018-07-12 | AM | Project WallBoard - Implementation | Practice | 4
[7 empty] | PM | Project WallBoard - Implementation | Practice | 4
[5 empty] | 4 | 2018-07-13 | AM | Project WallBoard - Implementation | Practice | 4
[7 empty] | PM | Project WallBoard - Implementation | Practice | 2
[8 empty] | Introduction exercise context for: BKH - Concepts (Topic: Surrogate key & Concurrent update, Application security) | Introdution | 1 |  | To give the trainee the context / scope before doing the exercise | Coach | 1
[8 empty] | Application security - Exercises | Self training | 1 | EB1
[5 empty] | 6 | 2018-07-14 | AM | Buffer for necessary training (JIRA, My ELCA) | Buffer | 0
3 | 5 | Backend + Project WallBoard |  | Service Desgin & Testing | 1 | 2018-07-16 | AM | Application security - Exercises | Self training | 1 | EB1
[8 empty] | Surrogate key & Concurrent update - Exercises | Self training | 2 | EB1
[7 empty] | PM | Unit testing in JAVA - Exercise | Self training | 4 | EB4
[8 empty] | SQL - Exercise | Self training | 1 | EB2 | Word version
[6 empty] | 2018-07-17 | AM | SQL - Exercise | Self training | 2 | EB2 | Word version
[5 empty] | 2 |  | PM | Project WallBoard - Implementation | Practice | 6
[6 empty] | 2018-07-18 | AM | Project WallBoard - Implementation | Practice | 2
[8 empty] | Q&A | Q&A | 2 |  | Check & explain BKH, Unit test, SQL | Coach | 2
[7 empty] | PM | Screen Live Test | Reading | 2 |  | Reading
[8 empty] | Project WallBoard - Screen Live Test & Correction | Practice | 2
[5 empty] | 3 | 2018-07-19 |  | Project WallBoard - Implementation | Practice | 8
[5 empty] | 4 | 2018-07-20 |  | Project WallBoard - Implementation | Practice | 8
[5 empty] | 6 | 2018-07-21 | AM | Buffer for necessary training (JIRA, My ELCA) | Buffer | 0
2 | 6 |  |  | Service implementation | 1 | 2018-07-23 | AM | Project WallBoard - Implementation | Practice | 8
[5 empty] | 2 | 2018-07-24 | AM | Project WallBoard - Implementation | Practice | 2
[8 empty] | Final Q&A | Q&A | 2 |  | Review & check + Code Inspection | Coach | 2
[8 empty] | Coding best practices (formal) | Practice | 2 |  | Reading
[7 empty] | PM | Project WallBoard - Correction after Q&A | Practice | 2
[5 empty] | 3 | 2018-07-25 |  | Project WallBoard - Correction after QHD's testing | Practice | 8
[5 empty] | 4 | 2018-07-26 | AM | Project WallBoard - Correction after QHD's testing | Practice | 8
[5 empty] | 5 | 2018-07-27 | AM | Project WallBoard - Correction after QHD's testing | Practice | 2
[8 empty] | Project WallBoard - Correction after QHD's testing | Practice | 2
[7 empty] | PM | Project WallBoard - Correction after QHD's testing | Practice | 4
[5 empty] | 6 | 2018-07-28 | AM | Buffer for necessary training (JIRA, My ELCA) | Buffer | 0
[8 empty] | Total hours |  | 240
[8 empty] | Trainer efforts |  | 6
[8 empty] | PHD |  | 0
[8 empty] | APL |  | 4
[8 empty] | QAN | HR | 0
[8 empty] | NTA | QM | 0
[8 empty] | ATN |  | 0
[8 empty] | QHD |  | 2
[8 empty] | DHN |  | 0
[8 empty] | Coach |  | 18
Formulas:
Date = [Date, row above]+1
Date = [Date, row above] +2